## Admin Ofc
Bldg 001
Admin Office
~ Interior SQFT = 260
Vinyl SF = 70
~ Interior Average Wall Height 9'-5"
Int/Ext | Repair Type | Yes/No | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ Door
Interior | Vinyl Floor Tile | N |  | Confirmed witrh SCUSD: Changing to Carpet
Interior | Paint | Y |  | Walls + Trim + Ceiling
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures Replaced | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Tiles Reattached and Painted | Y
Interior | Ceiling Dryrot | N
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Interior | Door Repair | N
Interior | Room Signage | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Provide & Install Room Signage | Y |  | Confirm Naming of Rooms
Exterior | Paint
Exterior | Window Replacement |  | X | Blinds - Remove & Re-install for Painting
Exterior | Provide & Install Columbine Hardware (1)

## Admin Clst
Bldg 001
Admin Closet
~Interior SQFT = 49
Carpet = 49
~Interior Average Wall Height = 8.0
Int/Ext | Repair Type | Yes/No | M&O Possibly Address? | Comments
Interior | Provide & Install New Carpet w/ Rubber Base | Y
Interior | Paint | Y |  | Walls + Trim + Ceiling (Hard Lid)
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures Replaced | N
Interior | Ceiling Painted |  |  | Hard Lid - Paint
Interior | Ceiling Dryrot | N
Interior | Casework Painted | Y
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Interior | Door Repair | N
Interior | Room Signage | N

## Nurse
Bldg 001
Nurse Office & Restroom
~ Interior Vinyl Floor SQFT = 240
Vinyl SF = 240
~ Interior Average Wall Height = 10' 4"
Int/Ext | Repair Type | Yes/No | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | New Vinyl Floor Tile | Y
Interior | Paint | Y |  | Walls + Trim + Ceiling
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures Replaced | N
Interior | Interior Electrical Panel Repair Work | N
Interior | T-Bar Ceiling Grid Repaired or Replaced | N
Interior | T-Bar Ceiling Acoustical Tiles | Y |  | 1 Tile Replaced, Rest Put in Place Up & Painted
Interior | Casework Painted | Y
Interior | Casework Repaired | Y |  | Adjust Doors
Interior | Casework Reattached | N
Interior | Door Repair | N
Interior | Room Signage | N
Interior | Rest Room - New Vinyl Floor | Y |  | Replace with New Vinyl (See Spec for District Standard, color TBD)
Interior | RR Fixture Repairs? | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Electrical Panel Repair | N
Exterior | Room Signage | N
Exterior | Paint | Y
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (1)

## Principal
Bldg 001
| Principal Office |  |  | Principal Bathroom
| ~Interior SQFT = 184 |  |  | ~Interior SQFT = 28
| ~Interior Average Wall Height = 12'-9" |  |  | ~Interior Wall Height = 12'-9"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide & Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ Door
Interior | Paint | Y |  | Walls + Trim + Case Work + Ceiliing Tiles
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures Replaced | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Tiles: Replace (2), Secure Remaining & Paint | Y |  | Replace 2, Secure Remaining & Paint
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Casework Painted | Y
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Interior | Restroom - Paint | Y |  | Walls + Trim + Ceiling
Interior | Restroom Exhaust Fan | N
Interior | Restroom Fixtures | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Room Signage | N
Exterior | Paint | Y
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N | X
Exterior | Provide & Install Columbine Hardware (1)

## Break Galley
Bldg 001
Admin - Break/Galley Kitchen
~Interior SQFT = 80
~Interior Average Wall Height = 8'3"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide & Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ Door
Interior | Paint | Y |  | Walls + Trim + Ceiling Tiles
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures Bulbs Replaced | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Reattach loose ceiling tiles | Y
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Casework Painted | Y
Interior | Casework Repaired | Y |  | Cabinet Door Adjustments Needed
Interior | Casework Reattached | N
Interior | Add Fridge? (Maybe have at Nicholas to bring over) | N
Interior | Door Repair | Y
Interior | Door Replaced | N
Interior | Signage | N
Exterior | Room Signage | N
Exterior | Wall Dry Rot | N
Exterior | Paint | Y
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (1)

## Kitchen Ofc
Bldg 002
MPR Kitchen Office/Storage
~Interior SQFT = 80
~ Interior Wall Height 8' 3"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Vinyl Floor | N
Interior | Provide & Install New Carpet w/ Rubber Base | Y
Interior | Paint | Y |  | Walls + Trim + Ceiling (Hard Lid)
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures Replaced | N
Interior | Exhaust Fan | N
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Casework Painted | Y
Interior | Casework Repaired | Y |  | Door Adjustments Needed on cabinets outside of Office/Storage Room
Interior | Casework Reattached | N
Interior | Door Repair | N
Exterior | Room Signage | N
Exterior | Paint | Y
Exterior | Window Replacement | N |  | Blinds - Remove & Reinstall for Paint

## MPR Kitchen
Bldg 002
MPR Kitchen
~ Interior SQFT = 500
~ Interior Wall Height = 9'
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Provide and Install Fire Extinguisher w/ Bracket | Y
Interior | Provide & Install Vinyl Floor | Y
Interior | Paint | Y |  | Walls + Trim + Ceiling Tiles
Interior | Electrical Outlets Added | N | X
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Tiles | Y |  | Replace (2) , Secure as needed & Paint
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Casework Painted | Y
Interior | Casework Repaired | Y |  | Tighten Handles
Interior | Casework Reattached | Y |  | Cabinet Door
Interior | Casework Removed | Y |  | Remove Metal Cabinet Over the Sink
Interior | Roll-up Door Repair | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Room Signage | N
Exterior | Paint | Y
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (1) | Y

## MPR Storage
Bldg 002
MPR Storage
~Interior SQFT = 200
~ Interior Wall Height = 9.6 Hard Lid
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Paint | Y |  | Walls + Trims + Ceiling (Hard Lid)
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures Replaced | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Hard Lid Repairs | N
Interior | Casework Painted | Y
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Interior | Door Repaired | N
Interior | Signage | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Room Signage | N

## MPR Breakroom
Bldg 002
MPR - Breakroom
~Interior SQFT = 280
~Interior Wall Height = 9.2
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Paint | Y
Interior | Provide & Install Vinyl Floor | Y
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures Replaced | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Hard Lid Repairs | N
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Interior | Door Repaired | N
Interior | Signage | N
Exterior | Door Repair | Y |  | Door Closure Repair
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Room Signage | N
Exterior | Provide & Install Columbine Hardware (1)

## MPR
Bldg 002
MPR
Interior SQFT = 2480
Stage SQFT = 1200 (In addition to)
Interior Wall Height = 20'
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Stage + Stairs next to Stage - 6 Steps (NOT Main Floor)
Interior | 4x4 Tile Squares to be Removed by Stage Steps, Leave as Concrete |  |  | Will be removed by HAZMAT/Demo
Interior | Paint (Main Area + Stage) | Y |  | Walls + Trim + Ceiling
Interior | Electrical Outlets Added | N | X
Interior | Electrical Outlets Relocated | N
Interior | Flourescent Light Fixture Bulbs Replaced with Provided & Installed Bulbs as Needed | Y |  | Both Main and Stage
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling (Main Area) - Smooth Texture & Paint | Y |  | Ceiling Tiles and Mastic will be removed by HAZMAT Contractor (NIC)
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Casework Painted (Stage) | Y
Interior | Casework Repaired (Stage) | N
Interior | Casework Reattached | N
Interior | Stage Elevator | Y |  | Confirm Operational, repair as needed. (Allowance)
Interior | Ice Machine | Y |  | Repair Plumbing Pipes as needed. (Allowance)
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Room Signage | N
Exterior | Paint | Y
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (3)

## Assmt Sht CR01
Bldg 003
CR 01
~Interior SQFT = 930
~ Interior Wall Height = 12'4"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling Tiles + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N | X
Interior | Light Fixtures Replaced | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Re-Attach Accoustical Tiles | N
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | Y
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint | Y
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR02
Bldg 001
CR 02
~Interior SQFT = 930
~ Interior Wall Height = 12'4"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling Tiles + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N | X
Interior | Light Fixtures Replaced | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Acoustical Tiles Secured | Y
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | Y
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint | Y
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR03
Bldg 001
CR 03
~Interior SQFT = 930
~ Interior Wall Height = 12'4"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling + Doors
Interior | Electrical Outlets Added | N | X
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Acoustical Tiles | Y |  | Replace 2, Secure as needed
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | Y
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Ramps/Stairs Repaired | N/A
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR04
Bldg 001
| CR 04 |  |  | Storage Room in CR 04
| ~Interior SQFT = 930 |  |  | ~Interior SQFT = 50
| ~ Interior Wall Height = 12'4" |  |  | ~Interior Wall Heigth = 8'6"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket | Y
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling Tiles + Doors
Interior | Electrical Outlets Added | N | X
Interior | Electrical Outlets Relocated | N
Interior | Light Fixture Bulbs Replaced | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Acoustical Tiles | Y |  | Re-Attach as Needed
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | Y
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Interior | Storage Room Paint | Y |  | Walls + Ceiling (Hard Lid)
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR05
Bldg 004
CR 05 (Set-up as a Library)
~Interior SQFT = 930
~Interior Average Wall Height = 12'4"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling Tiles + Doors (Not Casework)
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Tiles | Y |  | Replace 10, Secure as needed & Paint
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N/A
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR06
Bldg 004
CR 06 (Currently Set-up as a Library)
~Interior SQFT = 930
~Interior Average Wall Height = 12'4"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim (Not Tackable Surface and Not Ceiling Tiles) + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Accoustical DD Tiles Replaced | N |  | No Paint Needed - Looks Good
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N/A
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR07
Bldg 004
CR 07
~Interior SQFT = 930
~Interior Average Wall Height = 12'4"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim (Not Tackable Surface and Not Ceiling Tiles) + Doors
Interior | Electrical Outlets Added | N | X
Interior | Electrical Outlets Relocated | N
Interior | Light Fixture Bulbs Replaced as Needed | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Accoustical DD Tiles Replaced | N |  | Ceiling Looks Good - No Paint
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR08
Bldg 004
CR 08
~Interior SQFT = 930
~Interior Average Wall Height = 12'4"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket | Y
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim (Not Tackable Surface and Not Ceiling Tiles) + Doors
Interior | Electrical Outlets Added | N | X | Walls + Trim (Not Tackable Surface and Not Ceiling Tiles)
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures Replaced | N |  | Bulbs
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Tiles | Y |  | Secure Tiles as Needed
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | Y |  | 1 Door - Weather Strip Replaced
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR09
Bldg 005
CR 09
~Interior SQFT = 930
~Interior Average Wall Height = 12'4"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling Tiles + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N | X
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Tiles | Y |  | 5 Replaced, Secure as Needed
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | Y |  | (Currently Not Painted)
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR10
Bldg 005
CR 10
~Interior SQFT = 930
~Interior Average Wall Height = 12'4"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling Tiles + Doors
Interior | Electrical Outlets Added | N | X
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Tiles | Y |  | Secure as Needed
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | Y
Interior | Casework Repaired | Y
Interior | Casework Reattached | N
Exterior | Door Repair | Y |  | North side door needs to be repaired
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR11
Bldg 005
CR 11
~Interior SQFT = 930
~Interior Average Wall Height = 12'4"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling Tiles + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Tiles Re-Attach as Needed | Y
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | Y
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR12
Bldg 005
CR 12
~Interior SQFT = 930
~Interior Average Wall Height = 12'4"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling Tiles + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Tiles | Y |  | 1 Replace = Re-Attach as Needed
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | Y
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR13-B1
Bldg P09
CR 13 - B1
~Interior SQFT = 870
~Interior Wall Height = 8'5"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board |  | Y | To Be added By M&O
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Accoustical DD Tiles Replaced | N |  | T-Bar Grid - Looks Good
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Interior | Install New Blinds | Y |  | Replace (4)
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Dry Rot | Y |  | Dry Rot on Roof Soffit 2'x4' Area
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | Y |  | Replace Plywood on (2) Ramps
Exterior | Window Replacement | N |  | Replace Blinds 4 sets & Install after Paint
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR14
Bldg P01
CR 14
~Interior SQFT = 960
~ Interior Wall Height = 10'2"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling Tiles + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Flourescent Light Fixture Bulbs Replaced with Provided & Installed Bulbs as Needed | Y
Interior | Provide & Install New 2x4 LED Light Fixtures into new T-Bar grid. Quantity of 12 Fixtures | Y
Interior | Interior Electrical Panel Repair Work | Y |  | Panel Used as the Light Switch for Room - Provide and Install New Light Swith and New Panel Door
Interior | Provide & Install New T-Bar Grid & 2x4 Acoustical Tiles | Y |  | Ceiling has been removed, no demo needed
Interior | Ceiling Tiles | Y |  | Replace 1, Secure as Needed
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | Y |  | Remove walls, ceiling & fixtures. Cut & Cap all lines. Patch-back walls and paint with rest of room
Interior | Casework Painted | Y
Interior | Casework Repaired | Y |  | Handles
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Dry Rot | Y |  | NE Corner Trim Replacement
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (Qty 2)

## Assmt Sht CR15
Bldg P01
CR 15
~Interior SQFT = 960
~ Interior Wall Height = 10'2"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + New Ceiling + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Provide & Install New 2x4 LED Light Fixtures into new T-Bar grid. Quantity of 12 Fixtures | Y
Interior | Interior Electrical Panel Repair Work | N
Interior | Provide & Install New T-Bar Grid & 2x4 Acoustical Tiles | Y |  | Ceiling has been removed, no demo needed
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | Y |  | Replace 4 sheets of 4x8 floor plywood
Interior | Demo Restroom | Y |  | Remove walls, ceiling & fixtures. Cut & Cap all lines. Patch-back walls and paint with rest of room
Interior | Casework Painted | Y
Interior | Casework Repaired | Y |  | Repair Countertops (See Photo)
Interior | Casework Reattached | N
Interior | Roof Substrate Repair | Y |  | (See Photo)
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | Y |  | Dry Rot at Side of Window, Replace Rotted Roof Sheeting (See Photo)
Exterior | Open Electrical Conduit with Exposed Wires | Y |  | Remove and Cap (See Photo)
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (Qty 2) | Y

## Assmt Sht CR16
Bldg P01
CR 16
~Interior SQFT = 960
~ Interior Wall Height = 10'2"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures Replaced | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Repair | Y |  | Ceiling tiles will have been removed - Replace with Drywall & Paint
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | Y
Interior | Casework Repaired | N
Interior | Casework Reattached | N |  | Back wall is missing a cabinet
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N | X | 1 4x3.5 Panel - Just glass
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR17
Bldg P01
CR 17
~Interior SQFT = 960
~ Interior Wall Height = 10'2"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Accoustical DD Tiles Replaced | N |  | Looks Good, Paint Only
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | Y
Interior | Casework Repaired | Y |  | Edge of Countertop
Interior | Casework Reattached | N |  | None in Room
Exterior | Door Repair | N
Exterior | Door Replacement | Y |  | 2 Wood Doors Replaced
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR18
Bldg P02
CR 18
~Interior SQFT = 784
~Interior Wall Height = 10'2"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Tiles | Y |  | Re-Attached as Needed
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | Y
Interior | Casework Repaired | Y |  | 2 Handles Needed
Interior | Casework Reattached | N
Interior | Drapes | Y |  | Remove
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR19
Bldg P02
CR 19
~Interior SQFT = 784
~Interior Wall Height = 10'2"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Tiles | Y |  | Replace 4 + Secure As Needed
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | Y
Interior | Casework Repaired | Y |  | Replace Missing Handle
Interior | Casework Reattached | N
Interior | Drapes | Y |  | Remove
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Dry Rot | Y |  | 10' x 10' Area + Mod Seam Facia
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N |  | Drapes- Remove
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR20
Bldg P03
CR 20
~Interior SQFT = 900
~Interior Wall Height = 10'2"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket | Y
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Acoustical 2 x 4 Tiles | Y |  | Replace All Ceiling Tiles
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dry rot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N | X | No Electricity in Room - Investigate and Repair as Needed
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR21
Bldg P03
CR 21
~Interior SQFT = 900
~Interior Wall Height = 10'2"
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures Replaced | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Acoustical 2 x 4 Tiles | Y |  | Replace All Ceiling Tiles
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | Y |  | 1 Door
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N | X | 2 Broken Windows - 1 1X3, 1 3X4 / Blinds 4, Remove & Reinstall after Paint
Exterior | Remove Trees From Between Portables
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR22
Bldg P05
CR 22
~Interior SQFT = 960
~Interior Wall Height = 8'
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Acoustical 2 x 4 Tiles | Y |  | Replace 1 Tile
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Shelving Painted | Y |  | 18' x 6' of shelving (Not casework)
Interior | Casework Repaired | N
Interior | Shelving Reattached | Y |  | 18' x 6
Exterior | Door Repair | N
Exterior | Door Replaced | Y |  | 1- South Door
Exterior | Wall Dry Rot | Y |  | Hole Above Door, infill (See Photo)
Exterior | Electrical Repair | Y |  | Install Cap on Electrical Conduit (See Photo)
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | Y |  | Replace Plywood at Front & Back Doors (See Photos)
Exterior | Window Replacement |  | X | 1 Glass Panel 2'x3'
Exterior | Add Exterior LED Light at Back of Classroom | Y |  | Match Other RABs on Campus - Spec to be provided for RAB Fixture
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR23
Bldg P06
CR 23
~Interior SQFT = 960
~Interior Wall Height = 8'
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (2) Doors & Sink
Interior | Paint | Y |  | Walls + Trim + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures | N |  | 1 Lens replaced
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Acoustical 2 x 4 Tiles | Y |  | Remove and Replace all 2 x 4 Tiles
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | Y |  | Southwest corner (See Photo)
Interior | Demo Restroom | N/A
Interior | Casework Painted | Y |  | 6'x6' case work
Interior | Casework Repaired | N
Interior | Casework Reattached | Y |  | 6'x6' case work
Exterior | Door Repair | N
Exterior | Door Replaced | Y
Exterior | Wall Dry Rot | Y |  | Dry Rot at SW Trim & Corner (See Photo)
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | Y |  | Plywood Replaced on (1) ramp and (1) stairs (See Photo)
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (2)

## Assmt Sht CR24
Bldg P07
CR 24
`Interior SQFT = 600
~Interior Wall Height = 8'
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket | Y
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ Door & Sink
Interior | Paint | Y |  | Walls + Trim + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Modular Seam Trim Reattached - 30' | Y
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | Y
Exterior | Wall Dry Rot | Y |  | See Notes for Bldg P07 on CR 26
Exterior | Electrical Panel Repair | N
Exterior | Room Signage | N
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (1)

## Assmt Sht CR25
Bldg P07
CR 25
`Interior SQFT = 600
~Interior Wall Height = 8'
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket | Y
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ Door & Sink
Interior | Paint | Y |  | Walls + Trim + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Accoustical DD Tiles Replaced | N |  | Looks Good
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | Y |  | See Notes for Bldg P07 on CR 26
Exterior | Electrical Panel Repair | N
Exterior | Room Signage | N
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (1)

## Assmt Sht CR26
Bldg P07
CR 26
`Interior SQFT = 600
~Interior Wall Height = 8'
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket | Y
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ Door & Sink
Interior | Paint | Y |  | Walls + Trim + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures Repaired | Y |  | Add 2 x 4 lenses (10 Fixtures)
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Accoustical DD Tiles Replaced | N |  | Look Good
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | Y |  | Remove & Replace Siding: West Side 100 SQ FT. East Side 60 SQFT at bottom. South Side 120 SQFT. 45 SQFT at top. Remove & Replace S/W corner Trim.
Exterior | Electrical Panel Repair | N
Exterior | Room Signage | N
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (1)

## Assmt Sht CR27
Bldg P08
CR 27
~Interior SQFT = 960
~Interior Wall Height = 8'
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket | Y
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ Door & Sink
Interior | Paint | Y |  | Walls + Trim + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Reattach Mod Seam Trim | Y
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | Y |  | Remove and Replace Skirting: East Side 12 SQFT. South Side 60 SQFT. Remove and Replace Trim: South East Corner
Exterior | Electrical Panel Repair | N
Exterior | Room Signage | N
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (1)

## Assmt Sht CR28
Bldg P08
CR 28
~Interior SQFT = 960
~Interior Wall Height = 8'
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ Door & Sink
Interior | Paint | Y |  | Walls + Trim + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Light Fixtures Replaced | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Reattach Mod Seam Trim | Y
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | Y |  | Remove & Replace NW Corner Trim. Remove & Replace 60 SQFT of Skirt Siding with 2 Vents.
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (1)

## Assmt Sht CR33
(No Bldg #)
CR 33
~Interior SQFT = 960
~Interior Wall Height = 8'
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Tackable Surface | Y |  | Remove and Replace 8x8 Section
Interior | White Board | N
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ Door & Sink
Interior | Paint | Y |  | Walls + Trim + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlet Repair | Y |  | Repair - Falling off Wall
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Acoustical 2 x 4 Tiles | Y |  | Remove and Replace all Tiles
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N/A
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | Y |  | (1) Door
Exterior | Wall Dry Rot | Y |  | Remove and Replace: South Side 300 SQFT & East Side 60 SQFT
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement | N
Exterior | Provide & Install Columbine Hardware (1)

## Assmt Sht CRK1
Bldg 006
| CR K1 |  |  | Rest Room
| ~Interior SQFT = 900 |  |  | ~ 45 SQFT
| ~Interior Average Wall Height = 12'3" |  |  | ~Interior Wall Height = 10'
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install Fire Extinguisher w/ Bracket
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (3) Door & Sink
Interior | Paint | Y |  | Walls + Trim + Ceiling + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Tiles | Y |  | Replace 1- Re-Attach as Needed
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | New Restroom Vinyl Flooring | Y
Interior | Casework Painted | Y
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | Y |  | Weather strip needed (2) doors
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | N
Exterior | Electrical Panel Repair | N
Exterior | Provide & Install Room Signage | Y |  | One New Sign
Exterior | Paint | Y
Exterior | Ramps/Stairs Repaired | N
Exterior | Window Replacement |  | X | 1: Glass panel replace 16x36
Exterior | Provide & Install Columbine Hardware (3)

## Assmt Sht T-K (PreSchool)
Bldg P10
T-K (PreSchool)
~Interior SQFT = 1215
~Interior Wall Height = 8'
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior | Provide and Install Fire Extinguisher w/ Bracket | Y
Interior | Tackable Surface | N
Interior | White Board | N
Interior | Provide and Install New Carpet w/ Rubber Base | Y |  | Walk-Off Mat @ (3) Door & Sink
Interior | Paint | Y |  | Walls + Trim + Doors + Doors
Interior | Electrical Outlets Added | N
Interior | Electrical Outlets Relocated | N
Interior | Interior Electrical Panel Repair Work | N
Interior | Ceiling Acoustical 2 x 4 Tiles | Y |  | Replace (20) Ceiling Tiles
Interior | Ceiling Treated and Painted after Asbestos Tiles Removed | N
Interior | Ceiling Dryrot | N
Interior | Wall Dry Rot | N
Interior | Floor Dry Rot | N
Interior | Demo Restroom | N |  | Looks good
Interior | Casework Painted | N
Interior | Casework Repaired | N
Interior | Casework Reattached | N
Exterior | Door Repair | N
Exterior | Door Replaced | N
Exterior | Wall Dry Rot | Y |  | Remove & Replace: Entire East Side Paneling & Trim: 341 SQFT. Remove & Replace: South Side 204 SQFT. Remove & Replace: West Side 32 SQFT. Remove & Replace: Skirting Entire Building ~240 SQFT.
Exterior | Electrical Panel Repair | N
Exterior | Room Signage | N
Exterior | Paint | N
Exterior | Ramps/Stairs Repaired | Y
Exterior | Window Replacement | N
Exterior | Remove Wood Pergola Slats on North Side | Y
Exterior | Remove Porch Fencing on North Side & Replace with Ornamental Fence | Y |  | ~80' Long x 32" High
Exterior | Remove Trees from Between Portables | Y
Exterior | Provide & Install Columbine Hardware (3)

## Portable Restroom-Boys
Portable Restroom - Boys & Girls
Not Shown on Site Plan
~ Exterior Bldg SQFT = 600
~ Exterior Bldg. Height = 10'
Int/Ext | Repair Type | Yes = X | M&O Possibly Address? | Comments
Interior - Boys | Provide & Install Flooring Substraight - Assumed Plywood | Y |  | Removal of Substrate (NIC)
Interior - Boys | Provide & Provide & Install Vinyl Flooring | Y
Interior - Boys | Provide & Install FRP | Y |  | Replace (1) 4x8 FRP Section
Interior - Boys | Provide & Install New Partitions | Y |  | Removal of Partitions (NIC)
Interior - Boys | Provide & Install New Ceiling Tiles | Y |  | Removal of Ceiling Tiles (NIC)
Interior - Boys | Paint Ceiling Grid | Y |  | Paint Grid
Exterior - Girls | Exterior Door - Remove, Provide & Install New Metal Door | Y
Interior - Girls | Provide & Install New Ceiling Tiles | Y |  | Removal of Ceiling Tiles (NIC)
Interior - Girls | Paint Ceiling Grid | Y |  | Paint Ceiling Grid
Interior - Girls | Provide & Provide & Install Vinyl Flooring | Y
Interior - Girls | Provide & Install New Partitions | Y |  | Removal of Partitions (NIC)
Exterior - All | Paint | Y

## Exterior
Miscellaneous Exterior
Item | Repair Type | Yes = X | M&O Possibly Address? | Comments
1 | Tetherball Refresh (East) - Qty of 3 | Y |  | Provide & Install new Ball and Teather
2 | Tetherball Refresh (West) - Qty of 4 | Y |  | Provide & Install new Ball and Teather
3 | Volleyball Poles - Qty or 3 | Y |  | Remove & Provide and Install New Poles
4 | Basketball Backboards and Hoops Replaced - Qty of 4 | Y |  | Poles to Remain, Provide & Install new Backboards, Hoops & Nets
5 | Pressure Wash | Y |  | Complete Exterior of all Buildings including the brick
6 | Paint entire exterior of campus buildings including canopies and poles, excluding brink exterior | Y
7 | All Play Areas - Qyt of 3 | Y |  | Remove Existing Bark - Provide & Install New Park
| All Play Areas (3) - Pressure Wash |  | X
| All Play Areas (3) - Repair/Paint as Needed |  | X
8 | Site signage needed (Example: ADA Parking) | Y |  | Scope TBD - Covered by Owner Allowance
| Digital School Sign | N |  | Per CR: Remove
9 | Items to Demo & Remove | Y |  | Free standing structures in Pre-Shool Yard + West Aspahlt Area
| New Ornamental Entrance Fence | N |  | Approx. 50' Ornamental Heavy Fence w/Gate Buzzor (CR says to wait)
10 | Vinyl Privacy Slates added at Kinder Playground existing 5' high chainlink fence | Y |  | ~100 LF of Privacy slates only
11 | Remove Existing Drinking Fountain & Install OFCI Bottle Filler, Qty of 1, on South side of Portable Restroom Bldg and Qty of 1, on South side of P10 Pre-School Bldg. | Y |  | Provide Pick-up of Units from District Location. District Standard Spec will be Provided
12 | Paint Ornamental Fence Black ~ 650 LF | Y

## Perm Restrooms
Permanent Restrooms (4)
Repair Type | Comments
Paint | Walls (Including Tiles) + Ceiling (Hard Lids) Color TBD
Deep Clean