State and Federal Programs

2019-20 Private School Services Timeline/Checklist

| Month | Title I Activities | Title II Activities |
| --- | --- | --- |
| May/ June 2019 |  2019-20 Letter of Intent to Participate  SCUSD applies to CDE for federal funding |  2019-20 Letter of Intent to Participate  SCUSD applies to CDE for federal funding |
| August 2019 |  First Consultation meetings at school sites  Schools provided Initial Funding Allocation |  First consultation meeting at school site  Schools provided Initial Funding Allocation |
| Sept 2019 |  Deadline - 2019-20 Funding – Schools send student addresses for entire enrollment by September 30, 2019 to S& F Office.  2019-20 Title-I programs begin at school sites through Service Agreements or 3rd Party Provider Services if paperwork is submitted and approved. |  Submit 2019-20 Title II Professional Development Requests (upon receipt of Title II plan)- ongoing  Notify SCUSD to develop contract with 3rd party for ‘custom’ PD services |
| Oct 2019 |  2019-20 Funding - S & F Office returns student address lists to private schools identifying students in Title I school attendance areas  2019-20 Funding - Private Schools send home survey to students in Title I attendance areas  Deadline - 2019-20 Funding – Private School returns list of low income eligible students who are eligible for Title I services to S & F Office by October 31, 2019 |  Deadline for 2019-20 Title II Professional Development plan by October 31, 2019 (or due before requests)  Submit Title II Professional Development Requests- ongoing  Deadline - 2019-20 Funding – Total school enrollment by October 31,2019 |
| Nov 2019 |  Deadline - 2019-20 Title-I plans due to S & F Office by November 15, 2019  Deadline - Send 2019-20 (current year) Title I List of Students who will receive services to S & F Office by Nov 22, 2019.  Deadline - 2019-20 Service Agreements for tutors completed November 22, 2019 |  Submit Professional Development/Order Requests-ongoing  Deadline for 2019-20 Service Agreements and MOUs for 3rd party providers of professional development by November 26, 2019. |
| Dec 2019 |  |  Submit 2019-20 Title II Professional Development/Order Requests- ongoing |
| Jan 2020 |  Final allocation to schools, if applicable (date is subject to change) |  Submit 2019-20 Title II Professional Development/Order Requests-ongoing  Final 2019-20 allocation to schools if applicable (date is subject to change) |
| Feb 2020 |  |  Submit 2019-20 Professional Development/Order Requests- ongoing |
| March 2020 |  |  Review account balances and budget deadlines for submitting Order & Title II Travel Requests |
| April 2020 |  Deadline - Submit 2019-20 Title I Purchase Order (materials) Requests by April 12, 2019 | - Deadline – Final date to submit 2019-20 Professional Learning Requests that require a Service Agreement |
| May 2020 |  Invitation to Participate 2020-21 Forms are due  Deadline - Narrative Evaluation of 2019-20 Title I Program and pre/post assessment results due May 29, 2020 |  Deadline - Final date to submit 2019-20 Conference/Travel Request May 10, 2020 |